# Operational Plan

### Annual Project Work Plan Template Notes:

- Purpose: This template facilitates detailed planning and execution of annual project activities aligned with strategic goals.

- Flexibility: Adjust sections and details based on specific project requirements and feedback from stakeholders.

- Integration: Ensure integration with broader strategic plans and ongoing evaluation processes for continuous improvement.

2024 Projects:

- Circular Economies: Organ Meat Product Development

- Training Operational Coordinators for Co-op & Hub

- Community Benefits Programs: 807 Benefits & 807 Meals

- Northwestern Ontario Food Hub Network Project

Year: 2024-2025

Objectives:

- Build operational capacity with NOHFC Workforce development stream.

- Enhance Market Access, Promote Food System Sustainability and Foster Collaboration and Innovation through NWOFHN

- Strengthen Economic Resilience through Circular Economy Project and Community Benefits Programs

Key Deliverables:

- Branded Hub Product Utilising Organ Meats/Beef Scraps

  - Funded by: Grow Ontario Market Initiative (50%)

  - Target Completion Date: May 2025

  - Responsible Team Member(s): Bobbie Parr

  - Resources Required:

    - Product Development Contractor(s) ($9500)

      - Operational Plan

      - Promotional Content

      - Sales Funnel Creation

    - Marketing and Design Contractor ($9500)

      - Content Creation Plan

      - Content Folder & Funnel Design

      - Packaging / Product Logo

    - Facility and Storage Details

      - 5 days / month @ $300

      - $3000 one time fee

- Trained Operational Coordinators for Co-op & Hub

  - Funded by: NOHFC People and Talent: Workforce Development Stream

  - Target Completion Date: August 2025

  - Responsible Team Member(s): Bobbie Parr

  - Resources Required:

    - $70,000 Line of Credit

    - Paid Staff Member to supervise and evaluate

    - Onsite work and supervision plan

    - Contract requirements ($25/hr@35hours)

- NWOFHN Deliverables

- Recurring Revenue Strategies Applied by October 2024

Action Plan:

- Outline the action steps needed to achieve each deliverable.

- Assign responsibilities clearly to team members.

Resource Allocation:

- Detail how resources (financial, human, technological) will be allocated to support the action plan.

- Ensure alignment with the approved budget.

Monitoring and Evaluation:

- Describe the monitoring and evaluation framework.

- Include methods for tracking progress against targets.

- Specify intervals for review and adjustment of plans.

Partnerships and Stakeholder Engagement:

- Identify key stakeholders and partnerships critical for project success.

- Describe strategies for engagement and collaboration.

Risk Management:

- Identify potential risks and mitigation strategies.

- Assign responsibility for risk management tasks.

Reporting and Communication:

- Outline reporting frequency (e.g., monthly, quarterly).

- Specify formats for written reports and presentations.

Review and Approval:

- Define the process for reviewing and approving project milestones and adjustments.

- Include roles of the Operations Team, OCA, and 807 Board.

### Template for Quarterly Check-in Report

Reporting Period: [Quarter/Year]

Key Achievements:

- Summarize major accomplishments and progress toward annual objectives.

Challenges and Mitigation:

- Describe key challenges encountered and actions taken to mitigate them.

Adjustments to Plan:

- Note any adjustments made to the annual work plan and reasons for changes.

Financial Status:

- Provide an overview of financial expenditures against budget allocations.

Upcoming Priorities:

- Outline priorities for the next reporting period.

Recommendations:

- Offer recommendations for enhancing project effectiveness or addressing emerging opportunities.

Appendices (if applicable):

- Include additional data, charts, or detailed analyses supporting the report.

Approval:

- Signature of Project Lead and Operations Team approval.

### Quarterly Check-in Report Template Notes:

- Purpose: To provide a structured update on project progress and challenges.

- Alignment: Ensure alignment with annual objectives and strategic goals.

- Continuous Improvement: Use feedback from reports to refine future plans and strategies.